## Kanban
Backlog | To Do | In Progress | Review | Done
Purchase Lumber and Fasteners | Clear backyard site | Assemble deck frame | Inspect framing alignment | Select and Purchase Sealant / Stain
Purchase concrete for footings | Mark foundation layout | Install decking Planks | Check railing safety compliance | Install llighting fixtures
Check tool availability | Dig post holes | Apply protective sealant |  | Arrange labor team schedule
| Pour and cure concrete footings |  |  | Obtain Building Permits