## Power Interest Grid
Satisfy | Manage
High Influence, Low Interest | High Influence, High Interest
Local Government (Permit Office) | Homeowner (Project Sponsor)
Homeowners Association (HOA) | General Contractor
Monitor | Inform
Low Influence, Low Interest | Low Influence, High Interest
None | Neighbors
Subcontractors

## Stakeholder Register
Stakeholder Register
Stakeholder Designation | Name | Priority Grid |  | Risks | Strategy for managing risks | Communication Preference | Communication Info | Communication Notes | Additional Notes
|  | Power | Influence
Vendor | RT Contracting | High | High | 1. Won't install on time. 2. May try to increase price | 1. Clearly communicate schedule with 14 days advance notice. 2. Review quote prior to service. | Text | 111-222-3333 email@mail.com | Text 14 days before installation to review schedule and quote
Homeowner (Project Sponsor) | Ryan Tal | High | High | 1. Scope changes; 2. Budget concerns | 1. Regular progress updates; 2. Define clear budget limits | Weekly Meetings & Email | Ryan@maill.com | Review progress weekly | Keep informed on all changes
General Contractor | RT Contracting | High | High | 1. Won't install on time; 2. May try to increase price | 1. Clearly communicate schedule with 14 days advance notice; 2. Review quote prior to service | Text & Email | 111-222-4444, JD@RTcontracting.com | Text 14 days before installation to review schedule and quote | Coordinate weekly with Homeowner
Local Government (Permit Office) | City Permit Office | High | Low | 1. Delays in permit approvals | 1. Submit applications early; 2. Follow up regularly | Email & Phone | permits@city.gov, 555-333-4444 | Notify homeowner if additional documentation is required | Contact only when necessary
Subcontractors (Electricians, Plumbers, etc.) | Various | Medium | High | 1. Material shortages; 2. Scheduling conflicts | 1. Schedule work in advance; 2. Ensure availability of materials | Email & Phone | Various | Coordinate directly with General Contractor | Verify work quality
Neighbors | Local Residents | Low | High | 1. Noise complaints; 2. Parking issues | 1. Notify neighbors in advance; 2. Provide estimated schedule | Letter & Informal Meetings | N/A | Provide at least one-week advance notice | Address concerns promptly
Homeowners Association (HOA) | HOA Board | Medium | Medium | 1. HOA rule violations; 2. Possible fines | 1. Review HOA guidelines before starting; 2. Seek pre-approvals | Email | joe@hoa.com | Provide project plan for approval | Ensure compliance with HOA rules