## PROJECT
RESOURCE REQUIREMENTS
PROJECT DETAILS
PROJECT No: | MBDRP1
DATE: | 2025-02-10
FULL PROJECT NAME: | My Backyard Deck
PROJECT MANAGER: | Charlotte Josephine
PROJECT SPONSOR: | Emilie Doris

## RESOURCE REQUIREMENTS
RESOURCE REQUIREMENTS
ID | TYPE OF RESOURCE | RESOURCE DETAILS/SPEC | QUANTITY | LOCATION | SOURCE | ASSUMPTIONS | COMMENTS | DURATION | RISKS/MITIGATIONS
R001 | Person | Project Manager | 1 | Onsite | Staff | Responsible for overall project coordination. | Oversees timelines and budget compliance. | Entire project | Risk: Overlap of tasks. Mitigation: Use project management tools for scheduling.
R002 | Person | General Labor | 2 | Onsite | Staff | Required for physical tasks such as assembly and movement of materials. | Assist with repetitive tasks during construction. | 20 days | Risk: Labor shortage. Mitigation: Use local contractors as backups.
R003 | Person | Project Sponsor | 1 | Onsite | Staff | Ensures alignment with project goals and stakeholder needs. | Available for major approvals and critical decision-making. | Intermittent | Risk: Delayed approvals. Mitigation: Pre-schedule meetings for critical milestones.
R004 | Person | Designer - Smith | 1 | Offsite | Contractor | Prepares technical drawings and material specifications. | Provides expert recommendations on design feasibility. | 4 days | Risk: Design changes. Mitigation: Lock designs before permitting.
R005 | Equipment | Post Hole Dig | 1 | Onsite | Rent | Required for foundational digging tasks. | Ensure equipment is in good working condition prior to use. | 4 days | Risk: Equipment failure. Mitigation: Rent from a backup supplier.
R006 | Equipment | Tools - General | 1 | Onsite | Staff | Multiple tools for diverse construction tasks. | Inventory and confirm tool availability beforehand. | 30 days | Risk: Tool damage. Mitigation: Perform pre-use inspections.
R007 | Supplies | Deck Wood Material | 1 | Offsite | Home Depot | Key component for structural framing and flooring. | Verify quality and dimensions before purchase. | 30 days | Risk: Material defects. Mitigation: Order extra material for contingencies.
R008 | Supplies | Concrete | 1 | Onsite | Home Depot | Needed for foundational work. | Ensure proper mixing and curing for strength. | 12 days | Risk: Weather delays. Mitigation: Use covered storage and monitor weather forecast.
R009 | Supplies | Stain/Paint | 1 | Offsite | Home Depot | Chosen for durability and aesthetics of the deck. | Should match the selected wood and environmental conditions. | 14 days | Risk: Incorrect color. Mitigation: Test stain on a sample before applying.
R010 | Supplies | Fasteners | 1 | Onsite | Home Depot | Essential for joining structural elements securely. | Includes screws, brackets, and similar items. | 12 days | Risk: Shortage of fasteners. Mitigation: Purchase extras in advance.
R011 | Approval | Building Permit | 1 | Offsite | Govt | Required before construction begins. | Submit all required documentation promptly for approval. | 3 days | Risk: Delays in processing. Mitigation: Follow up with the permitting office.
R012 | Location | Backyard | 1 | Onsite | Staff | Space allocated for deck installation activities. | Ensure the area is cleared of debris and hazards prior to start. | 60 days | Risk: Site obstruction. Mitigation: Conduct a pre-construction site check.
R013 | Location | Garage | 1 | Onsite | Staff | Designated for storing tools and supplies securely. | Plan adequate space for equipment and materials to avoid delays. | 60 days | Risk: Lack of storage space. Mitigation: Optimize garage layout for materials.

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
RESOURCE ID
Give each resource requirement a unique identifier or reference so that it can be easily traced.
TYPE OF RESOURCE
Enter the type of the resource. For example, a person, machine, hardware or software, equipment, material, supplies and locations.
RESOURCE DETAILS/SPEC
Give the details of the resource required. Include product spec or skill set. Whatever is need to cost and source the resource.
QUANTITY
Give the number you will need to complete the project.
LOCATION
Enter the location of the resource, that might be an address, or whether the resource will work on or offsite.
SOURCE
Note where the resource will come from. For example, rental, contractor, member of staff.
ASSUMPTIONS
Include any assumptions that you have made about the resource. For example that they/it will be available.
COMMENTS
You can enter any extra notes about the resource here.