## Risk Register
Risk Register
Project Name: Ryan’s Backyard Deck Project
Project Manager: Charlotte Josephine
Date: February 15, 2025
ID | Risk Description | Likelihood | Impact | Risk Owner | Response / Mitigation Strategy
1 | Weather delays may halt foundation or staining | High | Medium | Project Manager | Monitor weather forecasts, schedule tasks in fair weather, use covered storage
2 | Permit approval delays from local authority | Medium | High | Project Manager / Sponsor | Submit applications early, follow up regularly, keep alternate start dates ready
3 | Labor shortages or contractor unavailability | Medium | High | Project Manager | Secure contracts in advance, keep backup contractors on call
4 | Material shortages or price increases | Medium | Medium | Supplier / Project Manager | Order extra wood and supplies early, lock pricing with suppliers
5 | Safety incidents during construction | Low | High | Carpenter (Site Lead) | Enforce PPE use, daily safety checks, clear site hazards
6 | Design changes requested mid-project | Medium | Medium | Client (Ryan Talbot) | Lock design before permitting, require formal change approval process
7 | Equipment/tool failure (post hole digger, drills, etc.) | Low | Medium | General Labor | Rent backup equipment, perform pre-use inspections
8 | Neighbor complaints (noise, parking, disruption) | Low | Low | Project Manager | Notify neighbors in advance, restrict noisy tasks to daytime hours
9 | HOA non-compliance or restrictions | Low | High | Project Sponsor | Review HOA guidelines, seek pre-approvals
10 | Budget overruns due to scope creep | Medium | High | Project Manager | Track costs weekly, require sponsor approval for >$500 changes

## Risk Report
Risk Report
Project Name: Ryan’s Backyard Deck Project
Project Manager: Charlotte Josephine
Date: February 15, 2025
Introduction
This report identifies potential threats and opportunities, evaluates their likelihood and impact, and outlines strategies to manage them. This ensures that stakeholders, including the project sponsor (Emilie Doris) and client (Ryan Talbot), understand the project’s overall exposure to risk and the plan to mitigate it.
Risk Identification
The project involves the construction of a 20x20 foot wooden deck, which includes foundation preparation, framing, decking installation, railing, and finishing. The risks fall into four main categories:
External Risks: Weather delays, permit approval, neighbor complaints, HOA restrictions.
Resource Risks: Labor shortages, contractor availability, equipment failure/malfunction, material shortages.
Financial Risks: Price fluctuations, budget overruns, scope creep.
Operational/Safety Risks: Safety incidents on site, design changes mid-project.
Risk Analysis
Each risk has been assessed in terms of its likelihood (Low, Medium, High) and impact (Low, Medium, High). The analysis shows the following priority risks:
1. Permit Approval Delays (M/H): Could halt the project start and push the schedule past March 2025.
2. Labor Shortages (M/H): Could prevent timely completion, especially if skilled trades are unavailable.
3. Weather Delays (H/M): Rain or freezing conditions could stall foundation and staining work.
4. Budget Overruns (M/H): Risks from scope creep or rising material costs could exceed the $10,000 baseline budget.
Other risks such as neighbor complaints, HOA restrictions, and equipment failure are lower in likelihood or impact but will be monitored.
Risk Response Strategy
Avoidance: Secure permits early to avoid delays; finalize designs before construction begins to prevent scope creep.
Mitigation: Order materials in advance, keep spare fasteners, maintain backup equipment rental agreements, and confirm labor availability.
Transfer: Where possible, transfer risks (supplier delivery guarantees, contractor performance clauses).
Acceptance: Minor risks such as neighbor complaints will be accepted, with mitigation through communication.
Risk Monitoring and Ownership
Each risk is assigned a risk owner responsible for monitoring and executing the response strategy:
Project Manager: Weather delays, budget tracking, material shortages, contractor availability, and stakeholder communication.
Project Sponsor: HOA compliance, permit issues.
Carpenter/Site Lead: On-site safety and tool/equipment functionality.
Client (Ryan Talbot): Scope changes and design approvals.
Risks will be reviewed at weekly project meetings, with updates logged in the risk register. Any new risks will be added promptly, and existing risks will be reassessed for severity.
Opportunities
In addition to threats, the project presents several opportunities:
Early Procurement: Buying materials early could lock in lower prices and ensure availability.
Stakeholder Engagement: Proactively informing neighbors and the HOA can build goodwill and reduce conflict.
Process Improvements: Using project management tools to track tasks and budgets enhances oversight and minimizes risk of overruns.
Conclusion
Ryan’s Backyard Deck Project carries a moderate to low level of risk typical of small-scale construction. With careful monitoring and proactive strategies, the most significant risks—permit delays, labor shortages, weather impacts, and budget overruns can be effectively managed. By following the risk register and implementing the outlined responses, the project remains feasible, on budget, and on track for timely completion.