## PROJECT
RESOURCE REQUIREMENTS
PROJECT DETAILS
PROJECT No: | BD1
DATE: | 01/01/xxxx
FULL PROJECT NAME: | Backyard Deck
PROJECT MANAGER: | C Bozic
PROJECT SPONSOR: | J Bozic

## RESOURCE REQUIREMENTS
RESOURCE REQUIREMENTS
ID | TYPE OF RESOURCE | RESOURCE DETAILS/SPEC | QUANTITY | LOCATION | SOURCE | ASSUMPTIONS | COMMENTS
R001 | Person | Project Manager | 1 | Onsite | Staff | C Bozic PM for project duration | PM to manage project
R002 | Person | General Labor | 2 | Onsite | Staff | Labor available each week to assist with heavy lifting and deck assembly. | 2 people for labor approx 4 hours for project duration
R003 | Person | Project Sponsor | 1 | Onsite | Staff | Project sponsor J Bozic needed for all approvals | Approve deck design, color, etc.
R003 | Person | Designer - Smith | 1 | Offsite | Contractor | Develop plans for deck | Plans appropriate for permit approval. Includes bill of material for wood.
R004 | Equipment | Post Hole Dig | 1 | Onsite | Rent | Rent from Bernard Tool Rental 1/10/xxx - 1/13/xx | Bozic to pick up
R005 | Equipment | Tools - General | 1 | Onsite | Staff | General tools needed for project duration | General Tools in inventory - hammers, screwdrivers, ladders, etc.
R006 | Supplies | Deck Wood material | 1 | Offsite | Home Depot | Wood package as sourced by Bill of Materials | Smith provided bill of materials for deck material with design plans.
R007 | Supplies | Connectors | 1 | Onsite | Home Depot | Assume local availability. | Use BOM to source nails, screws, brackets, etc.
R008 | Supplies | Stain | 1 | Offsite | Home Depot | Assume local availability. | Stain for deck color - not provided in BOM. PM and sponsor must select.
R009 | Approval | Building Permit | 1 | Offsite | Govt | Approval within 4 working days | PM to provide plans for permit and gain approval
R010 | Location | Backyard | 1 | Onsite | Staff | Deck install location - backyard | Location will be prepped for deck installation
R011 | Location | Garage | 1 | Onsite | Staff | Secure storage onsite for tools and materials | Securely store tools and materials when not in use. Car will be temporarily parked on street.

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
RESOURCE ID
Give each resource requirement a unique identifier or reference so that it can be easily traced.
TYPE OF RESOURCE
Enter the type of the resource. For example, a person, machine, hardware or software, equipment, material, supplies and locations.
RESOURCE DETAILS/SPEC
Give the details of the resource required. Include product spec or skill set. Whatever is need to cost and source the resource.
QUANTITY
Give the number you will need to complete the project.
LOCATION
Enter the location of the resource, that might be an address, or whether the resource will work on or offsite.
SOURCE
Note where the resource will come from. For example, rental, contractor, member of staff.
ASSUMPTIONS
Include any assumptions that you have made about the resource. For example that they/it will be available.
COMMENTS
You can enter any extra notes about the resource here.
This template was provided by
https://www.stakeholdermap.com/

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN STATUS FIELDS
Default settings
We have not set any drop down menus, as it is likely that most projects will have different priorities and categories.
How to create a drop down menu
Click on Data tab > Data Validation > Settings > List
In the Source field enter the menu items separated by a comma.
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings > List
ADDITIONAL FIELDS YOU MIGHT WANT TO ADD
Day rate
Total cost
Number of days needed
Dates needed
Dates available
Method used for estimating (quantities, duration, effort, cost)
Confidence level of estimating
Any constraints and risks associated with a resource
This template was provided by
https://www.stakeholdermap.com/